## Parameters
Project: | DBL HTI + webtech
Tasks |  | estimated effort(hours) | Participants |  | Budget
Task1 | Sprint Planning | 0.16667 | Student1 | Frederik Ondrikov | 1900-01-04 20:00
Task2 | Daily Scrum | 0.33333 | Student2 | Tessa van Beers | 1900-01-04 20:00
Task3 | Sprint Review | 0.16667 | Student3 | Bas Gerritsen | 1900-01-04 20:00
Task4 | Sprint Retrospective | 0.16667 | Student4 | Jay Benedicto | 1900-01-04 20:00
Task5 | Lectures/Plenary meetings | 0.083333 | Student5 | Lyuben Petrov | 1900-01-04 20:00
Task6 | Sprint Tasks | 1900-02-02 02:00 | Student6 | Nours Naama | 1900-01-04 20:00
Task7 | Sprint Task 1.1: research javascript, libraries, etc. |  | Student7 | Student7
Task8 | Sprint Task 1.1: look into data retrieval |  | Student8 | Student8
Task9 | Submit button --> one file at the time |  |  | Total budget | 1900-02-03
Task10 | Layout (simple)
Task11 | Client or server? --> research tutor
Task12 | Html file
Task13 | Retrieve data from upload file
Task14 | Look into libraries
Task15 | Research the data files
Task16 | Look into node links and adjacency matrix
Task17 | Research node.js
Task18 | Make a github
Task19 | Make the meeting digital
Task20 | Sprint Task x.x
| total estimated effort | 1900-02-03
| remaining budget: | 0
Formulas:
Budget = SUM(G5:[Budget, row above])
estimated effort(hours) = SUM(C5:[estimated effort(hours), row above])
estimated effort(hours) = G13-[estimated effort(hours), row above]
Note on B1: Enter project name here
Note on B5: Enter name of task here
Note on F5: Enter name of particpant here

## Student1
Tijdsregistratie | Frederik Ondrikov
| Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task
| Sprint Planning |  | 0.019444
| Daily Scrum |  | 0.0034722
Sprint Review
Sprint Retrospective
| Lectures/Plenary meetings | 0.083333
| Sprint Tasks | 0.125
| Sprint Task 1.1: research javascript, libraries, etc. |  | 0.125
Sprint Task 1.1: look into data retrieval
| Submit button --> one file at the time |  | 0.083333
Layout (simple)
Client or server? --> research tutor
Html file
Retrieve data from upload file
| Look into libraries |  | 0.041667
Research the data files
Look into node links and adjacency matrix
Research node.js
Make a github
Make the meeting digital
Sprint Task x.x
|  | 0.20833 | 0.27292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| hours spent | 0.20833 | 0.48125 | 0.48125 | 0.48125 | 0.48125 | 0.48125 | 0.48125 | 0.48125 | 0.48125 | 0.48125
| remaining hours | 1900-01-04 15:00 | 1900-01-04 08:27 | 1900-01-04 08:27 | 1900-01-04 08:27 | 1900-01-04 08:27 | 1900-01-04 08:27 | 1900-01-04 08:27 | 1900-01-04 08:27 | 1900-01-04 08:27 | 1900-01-04 08:27

## Student2
Tijdsregistratie | Tessa van Beers
| Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task
| Sprint Planning |  | 0.019444
| Daily Scrum |  | 0.0034722
Sprint Review
Sprint Retrospective
| Lectures/Plenary meetings | 0.083333
Sprint Tasks
| Sprint Task 1.1: research javascript, libraries, etc. | 0.125
| Sprint Task 1.1: look into data retrieval | 0.083333
Submit button --> one file at the time
| Layout (simple) |  | 0.25
Client or server? --> research tutor
| Html file |  | 0.041667
Retrieve data from upload file
| Look into libraries | 0.020833
Research the data files
| Look into node links and adjacency matrix | 0.020833
| Research node.js | 0.010417
Make a github
| Make the meeting digital | 0.041667 | 0.041667
Sprint Task x.x
|  | 0.38542 | 0.35625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| hours spent | 0.38542 | 0.74167 | 0.74167 | 0.74167 | 0.74167 | 0.74167 | 0.74167 | 0.74167 | 0.74167 | 0.74167
| remaining hours | 1900-01-04 10:45 | 1900-01-04 02:12 | 1900-01-04 02:12 | 1900-01-04 02:12 | 1900-01-04 02:12 | 1900-01-04 02:12 | 1900-01-04 02:12 | 1900-01-04 02:12 | 1900-01-04 02:12 | 1900-01-04 02:12

## Student3
Tijdsregistratie | Bas Gerritsen
| Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task
| Sprint Planning |  | 0.019444
| Daily Scrum |  | 0.0034722
Sprint Review
Sprint Retrospective
| Lectures/Plenary meetings | 0.083333
Sprint Tasks
| Sprint Task 1.1: research javascript, libraries, etc. |  | 0.25
Sprint Task 1.1: look into data retrieval
Submit button --> one file at the time
Layout (simple)
Client or server? --> research tutor
Html file
Retrieve data from upload file
Look into libraries
Research the data files
Look into node links and adjacency matrix
Research node.js
Make a github
Make the meeting digital
Sprint Task x.x
|  | 0.083333 | 0.27292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| hours spent | 0.083333 | 0.35625 | 0.35625 | 0.35625 | 0.35625 | 0.35625 | 0.35625 | 0.35625 | 0.35625 | 0.35625
| remaining hours | 1900-01-04 18:00 | 1900-01-04 11:27 | 1900-01-04 11:27 | 1900-01-04 11:27 | 1900-01-04 11:27 | 1900-01-04 11:27 | 1900-01-04 11:27 | 1900-01-04 11:27 | 1900-01-04 11:27 | 1900-01-04 11:27

## Student4
Tijdsregistratie | Jay Benedicto
| Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task
| Sprint Planning |  | 0.019444
| Daily Scrum |  | 0.0034722
Sprint Review
Sprint Retrospective
| Lectures/Plenary meetings | 0.083333 | 0.125
Sprint Tasks
| Sprint Task 1.1: research javascript, libraries, etc. | 0.25
Sprint Task 1.1: look into data retrieval
Submit button --> one file at the time
Layout (simple)
Client or server? --> research tutor
Html file
Retrieve data from upload file
Look into libraries
Research the data files
Look into node links and adjacency matrix
Research node.js
Make a github
Make the meeting digital
Sprint Task x.x
|  | 0.33333 | 0.14792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| hours spent | 0.33333 | 0.48125 | 0.48125 | 0.48125 | 0.48125 | 0.48125 | 0.48125 | 0.48125 | 0.48125 | 0.48125
| remaining hours | 1900-01-04 12:00 | 1900-01-04 08:27 | 1900-01-04 08:27 | 1900-01-04 08:27 | 1900-01-04 08:27 | 1900-01-04 08:27 | 1900-01-04 08:27 | 1900-01-04 08:27 | 1900-01-04 08:27 | 1900-01-04 08:27

## Student5
Tijdsregistratie | Lyuben Petrov
| Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task
| Sprint Planning |  | 0.019444
| Daily Scrum |  | 0.0034722
Sprint Review
Sprint Retrospective
Lectures/Plenary meetings
Sprint Tasks
| Sprint Task 1.1: research javascript, libraries, etc. |  | 0.20833
Sprint Task 1.1: look into data retrieval
Submit button --> one file at the time
Layout (simple)
Client or server? --> research tutor
Html file
Retrieve data from upload file
Look into libraries
Research the data files
Look into node links and adjacency matrix
Research node.js
Make a github
Make the meeting digital
Sprint Task x.x
|  | 0 | 0.23125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| hours spent | 0 | 0.23125 | 0.23125 | 0.23125 | 0.23125 | 0.23125 | 0.23125 | 0.23125 | 0.23125 | 0.23125
| remaining hours | 1900-01-04 20:00 | 1900-01-04 14:27 | 1900-01-04 14:27 | 1900-01-04 14:27 | 1900-01-04 14:27 | 1900-01-04 14:27 | 1900-01-04 14:27 | 1900-01-04 14:27 | 1900-01-04 14:27 | 1900-01-04 14:27

## Student6
Tijdsregistratie | Nours Naama
| Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task
| Sprint Planning |  | 0.019444
| Daily Scrum |  | 0.0034722
Sprint Review
Sprint Retrospective
| Lectures/Plenary meetings | 0.083333
Sprint Tasks
| Sprint Task 1.1: research javascript, libraries, etc. |  | 0.03125
| Sprint Task 1.1: look into data retrieval |  | 0.020833
Submit button --> one file at the time
Layout (simple)
Client or server? --> research tutor
Html file
Retrieve data from upload file
Look into libraries
Research the data files
Look into node links and adjacency matrix
Research node.js
Make a github
Make the meeting digital
Sprint Task x.x
|  | 0.083333 | 0.075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| hours spent | 0.083333 | 0.15833 | 0.15833 | 0.15833 | 0.15833 | 0.15833 | 0.15833 | 0.15833 | 0.15833 | 0.15833
| remaining hours | 1900-01-04 18:00 | 1900-01-04 16:12 | 1900-01-04 16:12 | 1900-01-04 16:12 | 1900-01-04 16:12 | 1900-01-04 16:12 | 1900-01-04 16:12 | 1900-01-04 16:12 | 1900-01-04 16:12 | 1900-01-04 16:12

## Student7
Tijdsregistratie | Student7
| Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task
Sprint Planning
Daily Scrum
Sprint Review
Sprint Retrospective
Lectures/Plenary meetings
Sprint Tasks
Sprint Task 1.1: research javascript, libraries, etc.
Sprint Task 1.1: look into data retrieval
Submit button --> one file at the time
Layout (simple)
Client or server? --> research tutor
Html file
Retrieve data from upload file
Look into libraries
Research the data files
Look into node links and adjacency matrix
Research node.js
Make a github
Make the meeting digital
Sprint Task x.x
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| hours spent | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| remaining hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Student8
Tijdsregistratie | Student8
| Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task
Sprint Planning
Daily Scrum
Sprint Review
Sprint Retrospective
Lectures/Plenary meetings
Sprint Tasks
Sprint Task 1.1: research javascript, libraries, etc.
Sprint Task 1.1: look into data retrieval
Submit button --> one file at the time
Layout (simple)
Client or server? --> research tutor
Html file
Retrieve data from upload file
Look into libraries
Research the data files
Look into node links and adjacency matrix
Research node.js
Make a github
Make the meeting digital
Sprint Task x.x
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| hours spent | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| remaining hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Totals
Totals and charts
| week1 | week2 | week3 | week4 | week5 | week6 | week7 | week8 | week9 | week10 | Totals | % Finished
Sprint Planning | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11667 | 70
Daily Scrum | 0 | 0.020833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.020833 | 6.25
Sprint Review | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Retrospective | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lectures/Plenary meetings | 0.41667 | 0.125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.54167 | 650
Sprint Tasks | 0.125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.125 | 0.36675
Sprint Task 1.1: research javascript, libraries, etc. | 0.375 | 0.61458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.98958
Sprint Task 1.1: look into data retrieval | 0.083333 | 0.020833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10417
Submit button --> one file at the time | 0 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.083333
Study | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25
Client or server? --> research tutor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Html file | 0 | 0.041667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.041667
Retrieve data from upload file | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Look into libraries | 0.020833 | 0.041667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0625
Research the data files | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Look into node links and adjacency matrix | 0.020833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.020833
Research node.js | 0.010417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.010417
Make a github | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Make the meeting digital | 0.041667 | 0.041667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.083333
Sprint Task x.x | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| week1 | week2 | week3 | week4 | week5 | week6 | week7 | week8 | week9 | week10 | Totals
Frederik Ondrikov | 0.20833 | 0.27292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.48125
Tessa van Beers | 0.38542 | 0.35625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.74167
Bas Gerritsen | 0.083333 | 0.27292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.35625
Jay Benedicto | 0.33333 | 0.14792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.48125
Lyuben Petrov | 0 | 0.23125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.23125
Nours Naama | 0.083333 | 0.075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15833
Student7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Student8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1899-12-31 02:15 | 1899-12-31 08:33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900-01-01 10:48
Formulas:
Totals = SUM([week1]:[week10])