## Sheet1
Wishes | To do | Doing | Done
Working on website | 1. Submit button --> one file at the time | Fred + Bas
Upload files | 2. Layout (simple) | Tessa
Translating data into visualisations | 3. Client or server? --> research tutor | Niklas
4. Front end developing
5. Back end developing
| 6. Html file | Tessa
| 7. Retrieve data from upload file | Nours
| 8. Look into libraries | All
| 9. Research the data files | Jay
| 10. Look into node links and adjacency matrix | All
| 11. Research node.js | Jay
| 12. Make a github | Nours